WASTEWATER/CAPITAL WATER PROJECT/REGULAR MEETING

DECEMBER 2, 2025

A Wastewater/Capital Water Project/Regular Meeting of the Town Board of the Town of Elizabethtown, County of Essex in the State of New York, was held at the Town Hall, 7563 Court Street, Elizabethtown, NY on December 2, 2025, and the public was welcome to attend.

PRESENT: Supervisor Reusser, Councilperson Allott, Greg Swart, Shannon Vogt, Hannah Neilly and Atty. Matt Fuller.

Start time: 1:35 PM

- Mr. Swart said the NBRC Grant for the Sewer project has been approved and will be available early next year. He felt that at the next meeting they should scope it out as there is monies in there for the easements.

- Discussed the contracts for water.

- Got the SPDES permit last summer and wants to talk to DEC to see where they are on this.

- WIIA has not come out yet but should be by end of year.

- Sewer is at 10% design and hopefully 30% next year.

- Regarding the Water Project, Mr. Swart showed some sketches of the project sites. Talked about some of the land issues. His goal is to get the report and planning moved along as far as possible. Biggest thing to do is to get the building layout done.

- Maps were shown and explained what they will do at the Kilburn site.

- Will need APA permitting because of wetlands and setbacks.

- Discussion on purchasing the land and not leasing. Need to talk to the property owner and then go from there. Will need an appraisal as a town can’t pay more than the appraisal. Discussion on what this would entail and the property.

- Showed maps of the sites and discussed decommissioning wells, transmission main, demo buildings and where main water sites would be.

- Discussed which site is potentially the best.

- Showed water line maps and the districts.

- Mr. Swart discussed with Water Superintendent Dickinson the problem areas.

- Getting reports organized and building layout drafted. Want to finalize the game plan as soon as possible next year.

- Next meeting is January 6, 2026

- Councilperson Allott asked about the 3rd well possibility. Need to have the well produce 250-300 or over gallons per minute.

- Test well on Fabian’s property will not be used because it had sediment.

- Mr. Swart will talk to Mr. Cormier next week regarding next steps.

This meeting was adjourned at 2:54 PM.

Respectfully submitted,

Janet E. Cross,

Town Clerk