Wastewater & Capital Water Project

Regular Meeting

September 1, 2026

A Wastewater & Capital Water Project/Regular Board Meeting of the Town Board of Elizabethtown, County of Essex in the State of New York, was held at the Town Hall, 7563 Court Street, Elizabethtown, New York on September 1, 2026, and the public was welcome to attend.

PRESENT: Supervisor Reusser, Councilperson Allott, Greg Swart, Hannah Neilly, Caroline Hillyard, Erin Hanczyk from Northern Forest and Leslie Karasin.

PRESENT VIA TEAMS: Attorney Matt Fuller, Councilperson Bailey, Shannon Vogt and Jessica Leerkes.

Meeting was called to order at 1:30PM.

- Greg Swart informed everyone that he revised the MP&R. He also revised the PER, including the engineer stamp on Environmental Report.

- Greg also mentioned that thirty percent of the design is complete but there will be a changes in how solid waste is handled.  He explained that because of more regulations on reed beds and the volume of waste the town would have, they will probably be looking at slug beds.

- He discussed how the slug beds would work.

- The town will need to do an updated bond resolution

2026 GRANTS:

Greg mentioned that the 2026 grants opened today.

- NYSEFC IUP Listing Update- IUP draft is out, town still qualifies for hardship.

- WIIA Grant is complete, awaiting award announcement.

- WQIP application opened today for Wastewater Treatment Plant, waiting to here on award results.  Town plans on applying for the collection system for Water Street and hospital/nursing home.  The other areas will be applied for in 2027.

- Town of Elizabethtown is officially Pro Housing certified.

- Climate Smart is ongoing with the goal to be bronze certified to receive more points for the 2027 WQIP application.

- Smart Growth is ongoing also.

- Awaiting results on the award for the NYS Resiliency grant which the town applied for in 2026.

NBRC PROJECT:

- Survey is complete, and came back last month

- Still working on design

- Mike Metcalf and Luke Borden from SDA will be coordinating with Paige for site inspections to locate septic systems on each property and do measurements.

- Going to work on some type of public notice so residents are aware of what the town is doing with the project and why they are going door to door to residents’ properties.

- Information can go on the town website and the Wastewater site also.

SDA:

Supervisor Reusser and SDA walked the effluent line site today. SDA will complete additional water modeling to provide designs to DEC to allow for a draft SDPES permit to be submitted to APA.

WATER PROJECT:

Supervisor Reusser also mentioned that the Kilburn property has fallen through.   The owner of the property is not interested in selling the property.  She has looked at other potential sites and will get back with everyone once she has more information.

Greg discussed that there is a viable piece of property off from Hurricane Road that is potentially available.  Greg must confirm with Claude for the exact location.

Greg discussed that Elizabeth Norman is the neighboring property and would allow easier accessibility to the other property so Supervisor Reusser will be contacting her and discussing the matter. Supervisor Reusser did talk to the property owner, and she is willing to work with the town.

Greg Swart mentioned that there are other properties along 9N west to Darling Lane that could possibly be viable properties to look at but none of those properties have been tested for water.

Supervisor Reusser mentioned that the only other properties that have been studied by Hydro Source is Noble Terrace but that was deeded as a park like the Footbridge and the parcel between Route 9 and the Boquet River but is not big enough for the 200-foot radius.

FUNDING UPDATE:

Hannah Neilly discussed the town’s funding.  The town currently has NYS EFC funding as well as the hardship grant.  Supervisor Reusser asked if water meters could be included in the grant.  Hannah Neilly and Greg Swart did say that they could be included but would have to include that in the grant process.

Meeting adjourned at 2:30PM.

Respectively Submitted,

Patti L Doyle

Town Clerk